## Sheet1
Sv | Product Backlog |  | Hanno's proposal for Items to consider
| Task | Redmine Issue(s) related to this | Item Lead | Team members involved | Non-team PI | User Story | Acceptance Criteria | Specifications | Documentation
ITEMS USED AS INPUT TO SPRINT 1.11 (Jan 14 - Feb 4)
1 | Ingest Raw BF data - Discuss the implementation and implement required functionality | #4020, 4047- 4051 | Adriaan | Jan David, Ruud, Nico | Fallows | As a support scientist/observer I need to: Ingest BF data to the LTA Need to tie-up the loose ends that came up with latest changes of the BF observation definition. | Ingest of Raw Beam Formed data
6 | CEP2 Data Managing System: Investigate what is needed and what is already available |  | Adriaan Alwin |  | Roberto | As a support scientist and observer I need the tools to a) display all used disk space in CEP 2 disks b) manage this disk space (in SCHEDULER at the moment)
9 | Investigate improvements to framework to enable Batch Scheduling and feedback of pipelines |  | Alwin | Wouter, Marcel |  |  |  |  | Replaces previous items on DPU and Batch scheduling
13 | Implement "Black box" Pulsar pipeline |  | Alwin | Alwin, Nico, Adriaan |  | Meeting held Sprint 1.11; define tasks for later implementation
14 | MSSS raw data "auto" archive: requirement workshop |  | Hanno |  |  | For HBA MSSS observations we also need to archive the raw data. Investigate whether this can be done in a pipeline fashion.
ITEMS THAT SHOULD BE ESTIMATED AND PRIORITISED FOR FOLLOWING SPRINTS
| Improve Storage Calculations (web applications) |  | Holties | Boelen (EXTERNAL will work flexibly) | Frieswijk, Pizzo | As a user/support scientist I need to: be able to calculate the expected data size of observations as they are: a) proposed (NorthStar) b) set-up (MoM-Scheduler) | a) Extension of existing calculators in Web/MoM with more user defined entries. b) Web page "Online Calculator" redesigned
| Discuss LTA ingest of other interferometry final data (e.g., catalogues, plots, except for images) |  | Adriaan | Form a group to define what are the final data! | Polatidis, Jozsa, Heald,Pizzo | As an support scientist I want to be able to ingest final products of interferometry data to the LTA (images catalogues, plots) , through MoM | a) Succesfully ingest final products of interferometry data to the LTA. b) Query (simple) of these datasets c) Download (e.g.FTP) the data from a user. |  |  | Reconsidee short term and long term needs for dataproducts that the LTA should support
| USER INGEST mechanism |  |  | Adriaan |  | As a user I need to be able to ingest my final products to the LTA | a) Succesfully Import processed Interferometry data b)Succesfully ingest final images c) Succesfully import processed PULSAR data
| Installation of LOFAR processing software outside CEP |  |  | Adriaan, Wouter
| Improve robustness LTA ingest pipeline |  |  | Adriaan
| LTA Ingest of processed beamformed data products |  | Adriaan |  | Fallows, Hessels | a) Pulsar pipeline products b) Dynamic Spectra
| Discuss Revision MoM-Northstar interface. Postponed for 1.12 |  | Hanno | Hanno, Nico | Frieswijk, Polatidis | As a support scientist I want to import all the characteristics of the observations as they have been proposed in Northstar to MoM. | 1) The fields in NorthStar should have a correspondence in MoM. 2) Successful transfer of all possible observing modes to a MoM Template (using example proposals) | Will define the specification during Sprint 1.7. It could be delayed given the evolution of XML script
| New Export-GUI for the LTA (EPIC) |  |  | Nico, Adriaan |  | As an support scientist I want to be able to use a GUI to ingest to the LTA, through MoM
Transfer maintenance of LTA UI (Astrowise) and related interfaces to ASTRON
| LTA Preview Images and Cutout Server | 3509 | Adriaan |  |  | Design the Cutout server implementation
Manually Pipeline process and ingest BF+correlated data products
Automatically Pipeline process and ingest BF+correlated data products
| LTA Ingest of TBB data |  | Adriaan | Alexander, Jan David, Nico | van den Aker, Schellart | We need to ingest TBB dumps to the LTA | a)Archive data b)Connect it to "paternal" observation if piggybacking c)Retrieval of data by User

## Sheet2
FINISHED RECENTLY
a) Enable NDPPP demixing in manual pipeline for MSSS b) Enable NDPPP demixing in manual pipeline for non-MSSS observation #3406 | Marcel | Marcel, Ger (b. #3406 recipe changed by Horneffer, verified ?) | Pizzo,(finishing?) | As a support Scientist I need NDPPP demixing to the manual pipeline to process old (existing) data and other data that will be observed in the next few weeks. | Successfully run in the “manual” pipeline
LTA ingest of raw interferometer and beam formed data | Adriaan | IN PROGRESS | Frieswijk, Fallows | As an support scientist I want to be able to ingest interferometry raw data and raw beamformed data to the LTA, through MoM | a) Successful ingest to the LTA of raw interferometry and Beam formed data, through MoM b) Query (simple) of these datasets c) Download (e.g. FTP) the data from a user.